## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Vijeta ,23696819
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board looks like …
|  | 3 | the game will have only one snake
|  | 4 | appreance of snake:it will be of green colour with red head
|  | 5 | the game will have one prey
|  | 6 | and prey look like as a smily face
|  | 7 | and its colour is yellow and every time its position should be different
|  | 8 | arrow keys should be used to control the snake
Left arrow:to move snake in left diretion and vice-versa for Right arrow
Up arrow:to control the snake in the upper direction and similarly for the bottom arrow
|  | 9 | to play the game firstly login form should appear
|  | 10 | the login form look like as a square box
|  | 11 | it ask for the authentication like the name and password to play the game
|  | 12 | if the authentication is correct then game board should display on the screen otherwise a message should appear that "information incorrect"
|  | 13 | game board has black color
|  | 14 | while playing the game whenever snake touches its body or whenever it hit to wall of the border then game should be finish
|  | 15 | and a message should be pop-up "Game-over"
|  | 16 | every time when snake eat smily its length should be increase
|  | 17 | with the passage of eating ,score should be increase
|  | 18 | after loosing game it display my name and my latest score
|  | 19 | and highest score always next to the gameboard until someone dose not break the record

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Vijeta,23696819
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | change the class name and Debugging errors |  |  | 1 | 100%
3 | uplode the all change in the repository |  |  | 2 | 100%
4 | Build the snake game as in the product backlog |  |  | 3 |  | 100%
5 | making abstract method |  |  | 3 |  | 100%
5.1 | in class :prey |  | GUI for gameboard | 3 |  | 100%
5.2 | :snake |  | GUI for login form | 3 |  | 100%
5.3 | :Game board |  |  | 3 |  | 100%
|  | Build the GUI |  | 3 |  | 100%
GUI for gameboard
GUI for login form
Building GUI for player
score
3.2 |  | Build the game logic
3.21
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%